## Budget
Category | Item | Budget | Committed | Paid | Remaining | Notes
Demolition & prep | Strip-out, skips, floor protection
Structural | Walls, beams, openings, engineer fees
Plumbing | First-fix, drainage, fixtures
Electrical | Rewire, sockets, lighting, certificates
Plaster & decorating | Plastering, paint, finishes
Kitchen / bathroom | Units, worktops, appliances, sanitaryware
Flooring & tiling | Materials and labour
Fees & permits | Design, building control, surveys
Contingency | Reserve for surprises (10-20% of the total)
TOTAL | [5 empty] | Remaining = Budget minus Committed

## How to use
How to use this template
Step 1 | Put every job or order on its own row and group them by category. Add rows as you go; the totals cover rows 2 to 24.
Step 2 | Fill in Budget when you plan the work, Committed when you accept a quote or place an order, and Paid when the money actually leaves your account.
Step 3 | Update it after every site visit or payment. A rough budget you keep current beats a perfect one you abandon in week three.
What each column means
Category | Plumbing, Electrical, Kitchen, and so on. Keep the list short enough that you actually use it.
Item | The specific job or order.
Budget | What you planned to spend.
Committed | Quotes you have accepted and orders you have placed. This is money you owe, even if you have not paid it yet.
Paid | Money that has actually left your account.
Remaining | Calculated as Budget minus Committed. Turns red if you go over.
Notes | Contractor, dates, anything you will forget in a month.
The one habit that matters | Track against Committed, not Paid. Budget minus Paid always looks healthy, because the money has not gone out yet. Budget minus Committed tells you the truth: an accepted quote is already spent. This single change is what turns a spreadsheet into an early warning system.
Contingency | Set aside 10-20% of your total budget as its own line before you start. Not "in case something goes wrong" but for when it does. Draw from it deliberately and write down what you used it for, or it disappears without you noticing.
Where a spreadsheet stops | It does not come to site with you, it has no cash-flow view, it ignores the schedule entirely, and one dragged cell can quietly break the totals. When those start to hurt, Storypole does the same thing as a live app.
Made with Storypole | A free renovation budget and schedule tracker that works offline with no account: storypole.app